## Feuil1
Tasks | Estimated Hours per task | Hours Spent-Day 1 | Hours Spent-Day 2 | Hours Spent-Day 3 | Hours Spent-Day 4 | Hours Spent-Day 5 | Hours Spent-Day 6 | Hours Spent-Day 7 | Hours Spent-Day 8 | Hours Spent-Day 9 | Hours Spent-Day 10 | Hours Spent-Day 11 | Hours Spent-Day 12 | Hours Spent- Day 13 | Hours Spent-Day -14 | Total Hours
Study Event Location | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Create a collection | 7 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 7
Front-end(forum post) | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 2.5
Template for forum | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 4
Uploading files | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Event cap | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
Click to join a private study | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Password Safety Handlers | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2
Correct password allows join | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2
Burndown Chart | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
Creating Permissions | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Testing | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
Change username in acc_set | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Rings layout | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Actual Remaining Hours | 31 | 28.5 | 28.5 | 27 | 24 | 23 | 22 | 20 | 18 | 17 | 16 | 15 | 13.5 | 11 | 3.5
Estimated Remaining Hours | 31 | 28.79 | 26.58 | 24.37 | 22.16 | 19.95 | 17.74 | 15.53 | 13.32 | 11.11 | 8.9 | 6.69 | 4.48 | 2.27 | 0
Task completed | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4