## Feuil1
Tasks | Estimated Hours per task | Hours Spent-Day 1 | Hours Spent-Day 2 | Hours Spent-Day 3 | Hours Spent-Day 4 | Hours Spent-Day 5 | Hours Spent-Day 6 | Hours Spent-Day 7 | Hours Spent-Day 8 | Hours Spent-Day 9 | Hours Spent-Day 10 | Hours Spent-Day 11 | Hours Spent-Day 12 | Hours Spent- Day 13 | Hours Spent-Day -14 | Total Hours
Acceptance test-sprint 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 4
Acceptance test-sprint 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3
Front-end(forum post) | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 4
Acceptance test-sprint 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2
events on dashboard | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2
burndown sprint 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
sprint 4-uncompleted | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 3.5 | 3.5
Actual Remaining Hours | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 18.5 | 17.5 | 15.5 | 11.5 | 7.5 | 0
Estimated Remaining Hours | 19.5 | 18.11 | 16.72 | 15.33 | 13.94 | 12.55 | 11.16 | 9.77 | 8.38 | 6.99 | 5.6 | 4.21 | 2.82 | 1.43 | 0
Task completed | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 5